## Sheet1
MOMBERGER AIRPORT INFORMATION Major Ongoing & Planned Airport Projects Updated: 20 July 2026 (updated bi-weekly)
REGION | COUNTRY | AIRPORT | IATA CODE | OPERATOR | PROJECT TYPE | GREENFIELD | PAX TRM | BHS | APM | CGO TRM | MRO | CAT | VIP/FBO/GA | ATC | FUEL | AIR-FIELD | LAND-SIDE | PROJECT DETAILS | CAPEX (MLLN USD) | REMARKS ON BUDGET ALLOCATION | STATUS | STATUS DETAILS | CONSULTANTS, ARCHITECTS, SUPPLIERS & CONTRACTORS | ADDED/UPDATED
09 Southeast Asia | Thailand | Bangkok-Suvarnabhumi (1) | BKK | Airports of Thailand (AoT) | Expansion |  | X | [10 empty] | Construction of boarding satellite: • 215,000 m² of floorspace • 28 contact stands • Raising capacity from 45 mppa to 60 million mppa | 1800 |  | Construction completed | Inaugurated in September 2024 |  | 2023-08-30
09 Southeast Asia | Thailand | Bangkok-Suvarnabhumi (2) | BKK | Airports of Thailand (AoT) | Expansion | [10 empty] | X |  | Third runway: • 3,700 metres • Increasing capacity to 90 ATMs per hour | 700 |  | Construction completed | Opened on 1 November 2024 |  | 2024-10-01
09 Southeast Asia | Thailand | Bangkok-Suvarnabhumi (3) | BKK | Airports of Thailand (AoT) | Expansion |  | X | [10 empty] | East Expansion Terminal: • 81,000 m² • Accommodating 15 million more passengers annually, raising the airport's total capacity from 65 million to 80 million passengers per year | 353 |  | Planning & design | Status details (as of 5 July 2026): • East Expansion remains on schedule for completion in 2031 | Master Plan: Netherlands Airport Consultants (NACO) – Lead consortium Terra Digital Ventures, Chotichinda, To70 – Planning and consultancy partners | 2026-07-05
09 Southeast Asia | Thailand | Bangkok-Suvarnabhumi (5) | BKK | Airports of Thailand (AoT) | Expansion | [10 empty] | X |  | Fourth runway | 800 |  | Planning & design | • Construction starts late 2027 and is expected to finish by 2035 • In March 2025, NACO was appointed to prepare a Master Plan and review all planned developments | Master Plan: Netherlands Airport Consultants (NACO) – Lead consortium Terra Digital Ventures, Chotichinda, To70 – Planning and consultancy partners | 2024-12-15
09 Southeast Asia | Thailand | Bangkok-Suvarnabhumi (6) | BKK | Airports of Thailand (AoT) | Expansion |  | X | [9 empty] | X | South terminal • Capacity of 55 mppa | 4200 |  | Planning & design | Status details (as of 5 July 2026): • South Terminal to be delivered in two overlapping phases between 2029 and 2039 | Master Plan: Netherlands Airport Consultants (NACO) – Lead consortium Terra Digital Ventures, Chotichinda, To70 – Planning and consultancy partners | 2026-07-05
09 Southeast Asia | Thailand | Bangkok-Suvarnabhumi (7) |  | Airports of Thailand (AoT) | Expansion |  | X | X | [9 empty] | Inbound BHS connecting T1 and Satellite 1 | 108 |  | Planning & design |  |  | 2025-08-23
09 Southeast Asia | Thailand | Bueng Kan | N/A |  | Greenfield | X | [11 empty] | New regional airport: • 400 hectares of land • Single 2,500 m runway | 235 |  | Planning & design | Status details (as of 10 May 2026): • Environmental approval received from National Environment Board • Project could be submitted to cabinet during 2026 • Construction planned to start in 2029 • Opening targeted for 2032 |  | 2026-05-10
09 Southeast Asia | Thailand | Chiang Mai | CNX |  | Expansion |  | X | [8 empty] | X | X | Expansion passenger terminal: • New international terminal • Existing terminal to be refurbished for domestic use • Capacity increase from 8 million to 16.5 million passengers per year Airside: • Expanded aircraft apron Landside: • Multi-storey car park with 1,100 spaces | 672 |  | Planning & design | Status details (as of 5 July 2026): • Expansion programme refined • Completion targeted for 2034 |  | 2026-07-05
09 Southeast Asia | Thailand | Chiang Mai-Lanna/Lamphun | N/A |  | Greenfield | X | [11 empty] | Second airport for Chiang Mai Phase 1: • New passenger terminal of 156,000 m² • Capacity of up to 24 million passengers per year • 38 aircraft stands • Designed for about 41 aircraft movements per hour Phase 2: • Two runways • Capacity of 40 mppa | 2000 |  | Planning & design | Status details (as of 8 March 2026): • In October 2024, a contract was signed with an unnamed consultant to conduct a six-month feasibility study • Feasibility study completed • Project is being prepared for cabinet approval • Detailed development and land acquisition would follow cabinet approval • Construction to start in 2027 • Scheduled to be opened by 2031 |  | 2026-04-04
09 Southeast Asia | Thailand | Chiang Rai | CEI | Airports of Thailand (AoT) | Expansion |  | X |  |  |  | X | [6 empty] | New passenger terminal + MRO centre: • Passengers terminal for 6m pax annually • MRO facility (assembly, disassembly, repair) on 8 ha | 158 | Terminal only | Planning & design | Status details (as of 23 August 2025): • Conceptual design under way, completion targeted 2032 |  | 2025-08-23
09 Southeast Asia | Thailand | Chumphon | CJM | Department of Airports | Expansion | [10 empty] | X |  | Airside: • Runway extension from 2,100 m to 2,990 m • Taxiway upgrades and apron expansion • Runway strengthening, safety areas and new airfield lighting systems | 45 |  | Pre-construction | Status details (as of 5 July 2026): • Design completed • Project has entered the procurement stage |  | 2026-07-05
09 Southeast Asia | Thailand | Hat Yai | HDY | Airports of Thailand (AoT) | Expansion |  | X | [9 empty] | X | Project details (5-year expansion): Near-term: • Departures hall renovation, restroom upgrades, • Access road works 3–5 years: • New terminal equiped with boarding bridges • Expanded car parks, 6-lane main access, 4-lane internal roads | N/A |  | Planning & design | Status details (as of 5 July 2026): • Master plan scheduled for completion during 2026 |  | 2026-07-05
09 Southeast Asia | Thailand | Kalasin | N/A |  | Greenfield | X | [11 empty] | Regional airport for Kalasin province, located in northeast Thailand | 60 |  | Feasibility | Status details (as of 10 May 2026): • Project remains at feasibility, design or environmental review stage |  | 2026-05-10
09 Southeast Asia | Thailand | Koh Samui | USM | Bangkok Airways | Expansion | [12 empty] | Terminal expansion: • Capacity to rise from 2 to 6 mppa | N/A |  | Planning & design |  |  | 2024-10-20
09 Southeast Asia | Thailand | Korat AB | N/A |  | Redevelopment |  | X | [8 empty] | X |  | Conversion of Korat Air Base into mixed-use airport, serving Nakhon Ratchasima, Thailand's third largest city | 69 |  | Feasibility | Feasibility study to take place during 2024 |  | 2024-03-30
09 Southeast Asia | Thailand | Krabi | KBV |  | Expansion |  | X | [10 empty] | Terminal and airfield expansion: • New Terminal 3 • Increasing passenger capacity from 4 mppa to 8 mppa • Improvements to existing terminals • New taxiway | 84 |  | Under construction | Project scheduled to be finished by late 2024 |  | 2023-08-30
09 Southeast Asia | Thailand | Mukdahan | N/A |  | Greenfield | X | [11 empty] | Construction of an airport in Kham Pa Lai subdistrict, Mueang District, Mukdahan province, on around 320 hectare of land 20 kilometres away from Mukdahan City | 147 |  | Planning & design | Status details (as of 10 May 2026): • Project remains at feasibility, design or environmental review stage |  | 2026-05-10
09 Southeast Asia | Thailand | Nakhon Pathom | N/A |  | Greenfield | X | [11 empty] | New regional airport in Nakhon Pathom province in central Thailand in Bang Len district and Nakhon Chai Sri district, 50 kilometres away from Bangkok: • 560 hectares of land • Single 2,500 metre runway | 737 |  | Planning & design | Status as of May 2025: • Feasibility study completed |  | 2025-05-04
09 Southeast Asia | Thailand | Nan | NAN |  | Expansion | [10 empty] | X |  | Airfield expansion: • Lengthening runway from 2,000 to 2,500 metres | N/A |  | Feasibility | Project scheduled to commence in 2027 and to be completed in 2030 |  | 2024-02-11
09 Southeast Asia | Thailand | Nan Nakhon | NNT | Airport Authority of Thailand (AoT) | Expansion |  | X | [8 empty] | X |  | Terminal and airfield expansion: • Runway extension from 2,000 to 2,300 m • Terminal expansion (300 → 1,400 pax/hr) • New 600-space parking lot | 106 |  | Planning & design | • Land acquisition: 2027–2029 • Construction starts: 2030 • Completion: 2032 |  | 2025-03-23
09 Southeast Asia | Thailand | Phang Nga-Andaman | N/A/ | Airports Authority of Thailand (AoT) | Greenfield | X | [11 empty] | New airport to supplement Phuket and Krabi airports, focussing on long-haul flights: Phase 1: • Passenger terminal with capacity of 22.5 mppa • One 3,300 metre runway • 44 aircraft stands • Designed for about 43 aircraft movements per hour Phase 2: • 2nd parallel runway • Total capacity of 40 mppa | 2000 |  | Feasibility | Status details (as of 8 March 2026): • In October 2024, a contract was signed with an unnamed consultant to conduct a six-month feasibility study • Feasibility study completed • Project is being prepared for cabinet approval • Detailed development and land acquisition would follow cabinet approval • Construction to start in 2027 • Scheduled to be opened by 2031 |  | 2024-10-20
09 Southeast Asia | Thailand | Phatthalung | N/A |  | Greenfield | X | [11 empty] | Regional airport in the southern province of Phatthalung | 87 |  | Planning & design | Status details (as of 10 May 2026): • Consultant procurement phase underway for design and environmental studies • Opening planned for 2033 |  | 2026-05-10
09 Southeast Asia | Thailand | Phayao | N/A |  | Greenfield | X | [11 empty] | Construction of regional airport in Dok Kham Tai district, around 18 kilometres from the city: • Single 2,500 metre runway | 116 |  | Feasibility | Status details (as of 10 May 2026): • Project remains at feasibility, design or environmental review stage | Design and environmental studies: Index International Group Public Company Limited, DK Consultant Company Limited and Enshi Company Limited | 2026-05-10
09 Southeast Asia | Thailand | Phuket | HKT |  | Expansion |  | X | [8 empty] | X |  | Expansion Phase 2: • International terminal expansion (+177,000 m²) • Runway/parallel taxiway extension; systems upgrades • Total capacity to rise from 12.5 to 18 mppa New support facilities (i.e. water supply, electrical system, and wastewater treatment plant) • Additional aircraft hangars | 277 |  | Planning & design | Status details (as of 10 May 2026): • Airports of Thailand reaffirmed Phase 2 expansion plans • Survey/design stage; construction start 2028; completion 2031 |  | 2026-05-10
09 Southeast Asia | Thailand | Roi Et | ROI |  | Expansion |  | X | [8 empty] | X |  | Terminal and airfield expansion: • Peak-time passenger capacity doubled to 600 passengers per hour • Security upgrades: dual-view X-ray scanners, explosives detectors • Runway extension from 2,100 to 2,500 metres | N/A |  | Planning & design | • Completion expected by 2030 |  | 2025-02-24
09 Southeast Asia | Thailand | Satun | N/A |  | Greenfield | X | [11 empty] | Regional airport in Satun Province in southern Thailand: • Covering 448 hectare of land in the Chebilang subdistrict in the Mueang district on 448 hectares of land | 121 |  | Feasibility | Status details (as of 10 May 2026): • Project remains at feasibility, design or environmental review stage |  | 2026-05-10
09 Southeast Asia | Thailand | Surat Thani | URT | Department of Airports (DOA) |  |  | X | [8 empty] | X |  | Modernisation and international upgrade: • New and expanded passenger terminal Landside: • Multi-storey car park • New access roads and elevated access structures Other facilities: • Supporting airport buildings | N/A |  | Planning & design | Status details (as of 4 January 2026): • Terminal expansion project progressing through development stages • Scheme intended to address capacity constraints and ageing facilities |  | 2026-01-04
09 Southeast Asia | Thailand | Trang | TST |  | Expansion |  | X | [8 empty] | X |  | Terminal and airfield expansion: • New passenger terminal • Extension runway from 2,100 metres to 2,990 metres | 44 |  | Under construction | • Runway project scheduled to be completed in January 2026 • Terminal delayed due to issues with contractor |  | 2024-11-09
09 Southeast Asia | Thailand | U-Tapao | UTP | Royal Thai Navy | Expansion |  | X |  |  |  | X |  |  |  |  | X |  | Expansion former Vietnam era US air force base and current LCC facility: Phase 1: • Construction of second 3,505 m runway • Revised plan with reduced first-phase terminal capacity from 12 million to 3 million passengers annually Other near-term developments: • MRO centre on approximately 33.6 hectares; Multi-type maintenance capability for Airbus and Boeing aircraft • Facilities to be operated under a long-term land lease • High-speed train connecting to Bangkok airports Long term: • Long-term passenger target reduced from 60 million to below 30 million annually | 8800 | Under revision | Pre-construction | Status details (as of 10 May 2026): • Project execution resumed following a contract management agreement signed on 29 January 2026 • Notice to Proceed expected within February 2026 • Second runway scheduled for completion in November 2028 MRO Facility: • Contract signing scheduled • Site management rights to be granted to Thai Airways International, with a subsidiary to be established to operate the centre • Delivery model to allow direct operation, joint ventures, or leasing to third-party operators • Environmental impact assessment being fast-tracked as a prerequisite to construction start Railway line: • Status details (as of 10 May 2026): • Government rejected proposed contract changes • Original conditions remain, including five-year construction period and reimbursement over ten years • Concessionaire may terminate the contract if it cannot proceed under current terms • Termination could delay the project by 8–10 years | Contractors/firms involved: • Concessionaire consortium: U-Tapao International Aviation (UTA) Co. Ltd, led by Bangkok Aviation Partners Co., Charoen Pokphand Group, BEM and China State Construction Engineering • Operating/technical partners: Flughafen München GmbH (Munich Airport), Narita International Airport Corporation • Runway: Italian-Thai Development (ITD) | 2026-05-10